## Resource scheduling
Pick d, ma, me, dev from the drop-downs to select the activity type
| Task (pick from the drop-down) | Duration (days) | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25
A | Assemble all new Parts | 1 | Pick d, ma, me, dev from the drop-downs to select the activity type 1: dev
B |  | #N/A
C |  | #N/A
D |  | #N/A
E |  | #N/A
F |  | #N/A
G |  | #N/A
H |  | #N/A
I |  | #N/A
J |  | #N/A
K |  | #N/A
Resource tracker
| Designers (d) [Designers design] |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Metrologists (me) [Metrologists measure] |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Development engineers (dev) [Assemble and test] |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Manufacturing takes time but doesn't require resouces as it is subcontract.

## Tasks and Durations
This sheet works as a look up table only.
There's no need to edit anything here!
Task | Duration (days)
Manufacture new 'Upper Torque Link' | 9
Measure new 'Lower Torque Link' | 1
Complete proof test of final assembly | 3
Measure new 'Steering sleeve' | 2
Design new 'Steering sleeve' | 1
Measure new 'Upper Torque Link' parts | 2
Manufacture new 'Lower Torque Link' | 4
Design new 'Lower Torque Link' | 3
Design new 'Upper Torque Link' | 3
Manufacture new 'Steering sleeve' | 2
Assemble all new Parts | 1